## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | User Login | Login | Admin, Manager, User | This is a screen which allows the user to enter username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Thắng | Done | iter1 | none
2 | User Register | Login | User | This is a screen which allows the user to register new account | Thắng | Done | iter1 | iter2 | Validate form when user enters details to reqister or when they login by username and password
3 | Forgot password | Login | User | This is a screen which allows the user to reset password for the case they forget it | Trọng | Done | iter1 | none
4 | Load Products and Category | HomePage | User | This is a screen which displays newest/best sell items, product/shop marketing | Thắng | Done | iter1 | none
5 | Product details | Home Page | User | This is a screen which displays products' details: quantity, size of product and quantity of that product in other agents | Hùng | Done | iter1 | none
6 | CRUD products | Manage | Admin, Manager | This is a screen which displays list of product in each agent, also there are pop-up form for manager and admin to insert/update or delete product | Khoa | Done | iter1 | iter2 | Fix after update database
7 | Filter product | Home Page | User | This is a screan which displays list of product according to category, season, price, size, gender | Thắng | Done | iter2 | none
8 | CRUD cart | Manage Cart | User | This is a screen where user can view, edit , delete or add more products they want into their card. | Hùng | Done | iter2 | none
9 | Submit cart to Order | Manage Cart | User | The user can reconfirm their cart. | Hùng | Done | iter2 | none
10 | View Order | Manage Order | Manager, Admin | This is a screen that manager and admin can view orders. Each manager in other agent can only view orders in that agent. Admin can view all | Khoa | Done | iter2 | none
11 | Update Status for Order | Manage Order | Manager, Admin | This is a screen that manager and admin can update status for orders. Each manager in other agent can only update status for orders in that agent. | Khoa | Done | iter2 | none
12 | Search Product by search bar | Search | User | This is a screen that display searched product according to inputted text | Thắng | Doing | iter3 | none
13 | Update User detail | Manage User detail | User | This is a screen that user can edit thier profile, etc | Trọng | Doing | iter3 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | User Login | Login | This is a screen which allows the user to enter username & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Thắng | Done | II.3 | III.5
2 | User Register | Login | This is a screen which allows the user to register new account | Thắng | Done | II.1 | III.4
3 | Forgot password | Login | This is a screen which allows the user to reset password for the case they forget it | Trọng | Done | II.1 | III.4
4 | Load Products and Category | HomePage | This is a screen which displays newest/best sell items, product/shop marketing | Thắng | Done | II.1 | III.4
5 | Product details | Home Page | This is a screen which displays products' details: quantity, size of product and quantity of that product in other agents | Hùng | Done | II.1 | III.4
6 | CRUD products | Manage | This is a screen which displays list of product in each agent, also there are pop-up form for manager and admin to insert/update or delete product | Khoa | Done | II.1 | III.4

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Filter product | Home Page | This is a screan which displays list of product according to category, season, price, size, gender | Thắng | Done | II.3 | III.5
2 | CRUD cart | Manage Cart | This is a screen where user can view, edit , delete or add more products they want into their card. | Hùng | Done | II.1 | III.4
9 | Submit cart to Order | Manage Cart | The user can reconfirm their cart. | Hùng | Done | II.3 | III.5
10 | View Order | Manage Order | This is a screen that manager and admin can view orders. Each manager in other agent can only view orders in that agent. Admin can view all | Khoa | Done | II.1 | III.4
11 | Update Status for Order | Manage Order | This is a screen that manager and admin can update status for orders. Each manager in other agent can only update status for orders in that agent. | Khoa | Done | II.1 | III.4

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
12 | Search Product by search bar | Search | This is a screen that display searched product according to inputted text | Thắng | Doing | II.3 | III.5
13 | Update User detail | Manage User detail | This is a screen that user can edit thier profile, etc | Trọng | Doing | II.1 | III.4

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4